## Table 1
Jun 26, 2024 ¦ SMGB Bi-Monthly Review
Attendees: Zahid Aziz Bahadar Ali gdodge@scanmygolfball.com tchase@scanmygolfball.com Ghazenfer
Mansoor Zubaria Fakhar Imran Noor Nadeem Ahmed Muhammad Haider Naeem Rao Moeed Munawar
Agenda
Agenda
Development Updates
Completed Tasks
* ROP records updated on Admin panel
* New design and updated flow for scanning screen with fit only and damage only
* Production release 2.0
In-Progress Tasks
* Implementation of scanning screen after design approval
Discussion Item
* Discussion of new design updates for scanning screen flow
* Discussion about potential tasks for SMGB project
Notes
* Damage design discussion:
* Variation 1 + Variation 2
* Minimum 2 images should taken for damage
* Move the options above scan button Maintain the state of last selected option for scan of user
* Change the camera logo from scan button to ball logo and add Start Scan text also
* After scan for damage, user should go back to Home Screen Pop up results of damage should be
shown over greyed out Home Screen
* There are two buttons one is Ok and another is Rescan. In Rescan user can do rescan and ok will
lead to home page
* user should go back to Scan screen
* 2 images for fit and 2 images for damage
* * * Damage threshold discussion:
* Damage results threshold should be 65%
* Handle the damage threshold from backend and provide option on admin panel for threshold
selection
* Future tasks discussion :
* Tasks will be prioritized soon after client discussion
Action items
* Need to share new prod build with updated damage threshold (Hot fix)
* Update the design as per client requirement
* Share the potential task for SMGB with client
Jun 12, 2024 ¦ SMGB Bi-Monthly Review
Attendees: Zahid Aziz Bahadar Ali Moeed Munawar gdodge@scanmygolfball.com
tchase@scanmygolfball.com Ghazenfer Mansoor Zubaria Fakhar Imran Noor Nadeem Ahmed
Muhammad Haider Naeem Rao
Agenda
Development Updates
Completed Tasks
Mobile App
* Updated the application flow for damage analysis with new labels
* Updated the texts for each label

## Table 2
* Removed the intercom from the mobile app
* Bug fixing
Reports
* Provided a report for Nyckel API brand and model identification
* Provided a report for Nyckel API damage analysis verification
Website
* Removed Intercom from the website
In-Progress Tasks
Designing
* UI designs for the scanning screen
Discussion Item
* Discussion on the image labeling mapping with the old labels
* Use case explanation
* Feedback Discussion on the Ball Recognition Model Report
* Discussion on the Externalizing the Ball Recognition API
* Discussion on Scanning button UI designs
*
Notes
* Feedback on the staging build
* Condition not available message shown
* Publish this version of the application to the production
* Feedback on UI design of scanning screen
* Create a stepper flow for scanning and use a single button for scanning
* Show a message “Do you want to do damage analysis”
* Yes/No
* If user selects Yes, Then user will be redirected to the scanning damage screen
* If user selects No, User will be redirected to the scanning result screen with showing results
accordingly
* Zubaria provide a UI demo for scanning button
* Keep the original button and show a popup on screen for Scan for ball brand and model and Scan
for Damage
* Use two options only
* Discussion on the Image labeling mapping
* Create new buckets for the new labels
* Leave the old labels
* Discussion on Discussion on the Externalizing the Ball Recognition API will be moved to next meeting
* TR team will share the ball recognition model report on the Slack and get feedback from the team
SMGB on slack
Action items
* Publish the current stage version to the production
* Share the release notes with the team SMGB
* Share the flow of the application on slack channel with team SMGB
* Share the ball recognition model on report on the slack channel and start communicating with team
SMGB on slack channel.